## Sheet1
Issue # | Description | Status | Status Date | Notes | Priority
1 | Add downsampling to convert large arrays of S parameters to smaller lengths for fast plotting | Complete | 2018-12-16 | Decimation completed, need to add low pass filter at some point | Moderate
2 | Connect S parameters to plotting scripts | Complete | 2018-12-16 |  | Moderate
3 | Add check for already open connections to prevent crashing | Open | 2018-12-17 |  | Moderate
4 | List connections on start up | Complete | 2018-12-16 |  | Moderate
5 | Add save and load capability for Edit Config | Open | 2018-12-17 |  | Low
6 | Log Settings to HDF5 | Complete | 2018-12-16 | Comments and COMport strings do not store properly | High
7 | Add units to elapsed time updates | Complete | 2018-12-16 |  | Low
8 | Reduce the number of digits of precision for time updates | Complete | 2018-12-16 |  | Low
9 | Increase PNA connection label length so the entire string is visible | Complete | 2018-12-16 |  | Low
10 | Get rid of extra spaces in calibration file name | Complete | 2018-12-17 |  | Moderate
11 | Add calibration control to the full PNA object | Complete | 2018-12-17 |  | High
12 | Test for calibration and stop measurement if not calibrated | Open | 2018-12-17 |  | Moderate
13 | Allow measurements to start without closing and reopening GUI | Open | 2018-12-17 |  | Moderate
14 | Clean up thread stopping for measurement thread | Open | 2018-12-17 |  | Moderate
15 | Delete incomplete HDF5 files when aborting a measurement | Open | 2018-12-17 |  | Low
16 | Fix issue with icons not showing | Complete | 2018-12-16 |  | Low
17 | Add icon for main application | Open | 2018-12-17 |  | Low
18 | Update help documentation and main Readme.md | Open | 2018-12-17 |  | Low
19 | Parse string in logging to convert newlines to <br> for HTML rendering | Complete | 2018-12-16 |  | Low
20 | Allow resizing of the GUI | Open | 2018-12-17 |  | Low
21 | Handle check for Stepper Motor expected position in the main window thread | Open | 2018-12-17 |  | Low
22 | Make sure the close window operation also stops the measurement thread | Open | 2018-12-17 |  | Moderate
23 | Move binaries and configuration to a common bin directory | Open | 2018-12-17 |  | Low
24 | Allow Edit Config to create a new configuration file with default parameters | Open | 2018-12-17 |  | Low
25 | Update the output file name when reloading the configuration | Complete | 2018-12-16 |  | Low
26 | Handle calibration in mock interfaces | Open | 2018-12-17 |  | Low
27 | Update Matlab version to write data in same locations as C++ version | Complete | 2018-12-18 |  | High
28 | Update data logger to be able to read settings | Open | 2018-12-17 |  | Moderate
29 | Fix issue with logging Comments to Settings attribute | Open | 2018-12-17 |  | High
30 | Fix issue with logging COMPort to Settings attribute | Open | 2018-12-17 |  | High
31 | Add menu item to select ploting real and imaginary or magnitude and phase | Open | 2018-12-17 |  | Low
32 | Add version to Matlab data reader to allow it to read both new and old versions of data | Complete | 2018-12-17 |  | High
33 | Add reset Stepper Motor position when starting a measurement | Open | 2018-12-17 |  | Low
34 | Query Stepper Motor device string | Complete | 2018-12-17 | Empty string returned, no true device id available | Low
35 | GUI crashing on exiting | Complete | 2018-12-17 | Trying to stop and delete the stepper motor timer caused the crash | High
36 | Add exception handling in measurement thread | Complete | 2018-12-17 |  | Low
37 | Add exception handling to data logger to include HDF5 exceptions | Open | 2018-12-17 |  | Low
38 | Close the HDF5 file after completing measurements | Complete | 2018-12-17 |  | High
39 | Fix issue with calibration check always returning true | Open | 2018-12-17 |  | Moderate
40 | Add low pass filter to signal decimation | Open | 2018-12-17 |  | Low
41 | Update Settings data logging to not require open file | Open | 2018-12-17 |  | Moderate
42 | Move Settings data logging to separate files for clarity | Open | 2018-12-17 |  | Moderate
43 | Have Calibration set the mode properly | Open | 2018-12-17 |  | Low
44 | Need to reset the parameters of the PNA after performing a cal - should be the start of measurement | Open | 2018-12-17 |  | High
45 | Add error icon | Open | 2018-12-17 |  | Low
46 | Allow GUI to select the calibration file on the PNA | Open | 2018-12-17 |  | Low
47 | Add measurement realization counter to the status bar | Open | 2018-12-17 |  | Low
48 | Change gated measurement name to real and imag are on the end to simplify Matlab data loading | Complete | 2018-12-18 |  | Moderate
49 | Change Matlab Settings logging to HDF5 file to use Settings group to match C++ version | Complete | 2018-12-18 |  | Moderate
50 | Change Matlab to read the new Settings/config file | Complete | 2018-12-18 |  | Moderate
51 | Change Matlab print Settings for the new Settings structure | Open | 2018-12-18 |  | Moderate